## Sheet1
Req ID | Requirement Description | Sprint | Requirement Type | Design | Development | Testing | Test ID | Test Result | Deployment | Comments
RQ1 | Student Registration & Login | Sprint 1 | Functional | Completed | Completed | Completed | TC‑01-04 | Passed | Completed
RQ2 | Employer Registration & Login | Sprint 1 | Functional | Completed | Completed | Completed | TC‑05-06 | Passed | Completed
RQ3 | Basic Student Profile | Sprint 1 | Functional | Completed | Completed | Completed | TC‑07 | Passed | Completed
RQ4 | Basic Job Post Creation | Sprint 1 | Functional | Completed | Completed | Completed | TC‑09 | Passed | Completed
RQ5 | Upload CV | Sprint 1 | Functional | Completed | Completed | Completed | TC‑08 | Passed | Completed
RQ6 | View Job Listings | Sprint 1 | Functional | Completed | Completed | Completed | TC‑10 | Passed | Completed
RQ7 | Application Status Tracking | Sprint 2 | Functional | Completed | Completed | Completed | TC‑9-10 | Passed | Completed
RQ8 | Filter Applicants | Sprint 2 | Functional | Completed | Completed | Completed | TC‑7 | Passed | Completed
RQ9 | View Applicants | Sprint 2 | Functional | Completed | Completed | Completed | TC‑5-6 | Passed | Completed
RQ10 | Reject/Shortlist Applicants | Sprint 2 | Functional | Completed | Completed | Completed | TC‑9-10 | Passed | Completed
RQ11 | Edit Job Listings | Sprint 2 | Functional | Completed | Completed | Completed | TC‑11 | Passed | Completed
RQ12 | Apply For Job: B | Sprint 2 | Functional | Completed | Completed | Completed | TC‑1-4 | Passed | Completed
RQ13 | In-App Notifications | Sprint 3 | Functional | Not Started | Not Started | Not Started | TC‑17 | - | Not Started
RQ14 | Save Jobs | Sprint 3 | Functional | Not Started | Not Started | Not Started | TC‑18 | - | Not Started
RQ15 | Analytics For Employer | Sprint 3 | Functional | Not Started | Not Started | Not Started | TC‑19 | - | Not Started
RQ16 | Skill-Based Job Matching | Sprint 3 | Functional | Not Started | Not Started | Not Started | TC‑20 | - | Not Started
RQ17 | Job Search by Keyword | Sprint 4 | Functional | Not Started | Not Started | Not Started | TC‑21 | - | Not Started
RQ18 | Mobile Optimization | Sprint 4 | Functional | Not Started | Not Started | Not Started | TC‑22 | - | Not Started
RQ19 | Enhance Job Listings Display Page | Sprint 4 | Functional | Not Started | Not Started | Not Started | TC‑23 | - | Not Started
RQ20 | Final Testing & Deployment | Sprint 4 | Functional | Not Started | Not Started | Not Started | TC‑24 | - | Not Started